Science Implementation Plan

Elementary (PK-4)

2011 - 2014

| Goals: Grades PK-4 1) Grade 4: Maintain or exceed mastery of ALL students on NYS Science Assessment from 65%-67% by 2014. 2) Grade 4: Maintain or exceed proficiency of ALL students on NYS Science Assessment from 96%-98% by 2014. 3) Grade 4: Maintain or exceed 72% proficiency of SWD on NYS Science Assessment by 2014. |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| What | How | Professional Development | Who | Time-Line | Support | Responsibility | Evaluation | Next Steps |
| Step-by-Step plan | Major Tasks |  | Target Population | Dates | Funding Sources | Who Does It? | POST- How did it go? | PLAN- What are the next steps? |
| Curriculum: 1) Curriculum Alignment (annually, align, prioritize, and spiral content and skills based on internal and state data) 2) Literacy 3) Scientific Method | 1a) Finish creating curriculum maps including aligned skills and align them (horizontally and vertically) 1b) Begin aligning CCSS science literacy skills to maps 1c) Annual data deconstruction and align to assessments 2a) Disseminate vocabulary lists and definitions to grade levels 2b) Share best practice for science literacy horizontally and vertically 2c) Incorporate expository text into instruction, explicitly targeting graphs and data tables 3) Incorporate open-ended, inquiry based learning into instruction | 1a-c) Work with Science BOCES facilitator to examine and interpret CCSS horizontally and vertically as well as annual data deconstruction 2a) PK-12 Science Facilitator Team will align and share the lists with grade levels at grade level meetings 2b) Science BOCES facilitator will investigate and share best practice in science with PK-12 Science Facilitator Team 2c) Collaborate with Literacy Specialists to integrate more expository text into instruction 3) BOCES Facilitator will bring resources and assist science facilitators with designing and locating activities that support inquiry based learning | PK–4 teachers | PK-12 Science Facilitator Team 4x/yr Grade Level Meetings (Monthly) | District Budget | Assistant Superintendent of Curriculum and Instruction, Principals, Assistant Principals, District TOSA, BOCES Facilitator, Science Facilitators, TIFS, Instructional coaches, Assessment Coordinators |  |  |
| Assessment: 1) Common assessments | 1) Evaluate effectiveness and implementation of curriculum utilizing common formative and summative assessment data | 1) Share and analyze results of common assessments vertically and horizontally as well as across buildings | PK–4 teachers | PK-12 Science Facilitator Team 4x/yr Grade Level Meetings (Monthly) | District Budget | Assistant Superintendent of Curriculum and Instruction, Principals, Assistant Principals, District TOSA, BOCES Facilitator, Science Facilitators, TIFS, Instructional coaches, Assessment Coordinators |  |  |
| Instruction: 1) Implement best practice in science instruction | 1) Research and identify best practice in science instruction PK-4 (including but not limited to technology integration, 21st century skills, reading in the content area, literacy strategies and vocabulary) | 1) Training on best practice in science, technology integration, and literacy from internal and external expert in elementary science instruction, literacy specialists, technology specialists | PK–4 teachers | PK-12 Science Facilitator Team 4x/yr Grade Level Meetings (Monthly) | District Budget | Assistant Superintendent of Curriculum and Instruction, Principals, Assistant Principals, District TOSA, BOCES Facilitator, Science Facilitators, TIFS, Instructional coaches, Assessment Coordinators |  |  |